## Sheet1
item | row_type | date_added | time_est_lb | time_est_ub | time_irl | notes
Getting (re)oriented, facelift for the MEA acute | item | 2023-02-27
Compiling to-do list, figuring out if need to read lab notebook | entry | 2023-02-27 |  |  | 1.2
Read through lab notebook for all well quality notes | item | 2023-02-24 | 0.5 | 2 | 3.5
Determine which cultures and plates to use | item | 2023-02-24 | 3 | 10
Work issues identified from lab notebook | item | 2023-02-24 | 3 | 20
Finalize implementation of fool-proof method to differentiate baseline from treated recording | item | 2023-02-24 | 1 | 3
Run through run_me script, address bugs as they arise | item | 2023-02-24 | 1 | 20
Implement conc, compound, and wllq checking I've developed for other assays | item | 2023-02-24 | 3 | 7
Get a sense of how bad the baseline decline and/or DMSO effect is compared to historical data (and in general). Is the data release-able? | item | 2023-02-24 | 2 | 5
Other QC Analyses | item | 2023-03-03 | 4 | 15

## time_log
date | largest_category | detail | time_spent
2023-05-11 | run_me clean, debug, & run |  | 4.57
2023-05-11 | sample ID investigation |  | 0.52
2023-05-15 | Finalize implementation of fool-proof method to differentiate baseline from treated recording |  | 1.78
2023-05-22 | run_me clean, debug, & run |  | 1.37
2023-05-23 | run_me clean, debug, & run |  | 0.55
2023-05-24 | run_me clean, debug, & run | finalizing culture.date discrepancies; created function to read raw CTB data; worked on identifying all LDH/cyto files | 1.3
2023-05-25 | run_me clean, debug, & run | finalized functions to read all raw CTB and LDH files and clean that data table; updated level 2 function | 4.42
2023-05-26 | run_me clean, debug, & run | Updated lvl 2 function, updated traditional cytotox reading functions. Def not my most productive time | 1.17
2023-06-05 | run_me clean, debug, & run | Resolving discrepancies between raw and Calculations files cytotoxicity data | 2.42

## Totals
time_lb | time_ub
17.5 | 82 | hours
3.5 | 16.4 | days (full court press)